## P & F Progress Phase-II (hidden)
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
HIGH VOLTAGE DISTRIBUTION SYSTEM (HVDS)
Physical & Financial Progress of HVDS Phase-II works awarded on PTK basis as on 31.01.2018
Sl. No. | Name of Division | Name of the Sub Division | Name of the firm | Awarded Cost (Rs. in Crores) |  |  | DWA issued on | No. of feeders Proposed | No. of Feeders Completed & Commissioned | No. of feeders work under progress | No. of feeders work to be taken up | Expenditure Incurred (Rs. in Crores) |  |  |  | Remarks
|  |  |  | BESCOM portion | DWA Cost (Agency) | Total | [5 empty] | BESCOM Portion | Agency Portion | Total | % Progress of Agency portion
1 | Kanaka pura | Kanakapura Urban | M/s. SPR Construction, Hyderabad | 20.44 | 24.14 | 44.58 | 04.12.2015 | 14 | 13 | 1 | 0 | 21.59 | 20.24 | 41.83 | 83.84% | Work under Progress | 49.87
2 |  | Kanakapura Rural | M/s. Raja Electricals, Tumkur | 15.64 | 20.37 | 36.01 | 20.11.2015 | 10 | 9 | 1 | 0 | 13.52 | 16.42 | 29.94 | 80.61% | Work under Progress | 39.59
3 |  | Harohally | M/s. Shivachetana Electricals, Sindhanur | 14.68 | 20.03 | 34.71 | 06.10.2015 | 14 | 7 | 6 | 1 | 10.03 | 9.72 | 19.75 | 48.53% | Work under Progress | 38.66
4 |  | Sathnur | M/s. Sri Manju Electricals, Tumkur | 12.28 | 17.05 | 29.33 | 06.10.2015 | 11 | 5 | 4 | 2 | 8.46 | 8.31 | 16.77 | 48.74% | Work under Progress | 31.74
5 | Tumkur | Huliyurdurga | M/s. Sri. Lakshmi narasimha Electricals, Tumkur | 10.48 | 16.65 | 27.13 | 06.10.2015 | 12 | 11 | 0 | 1 | 9.17 | 11.92 | 21.09 | 71.59% | Work under Progress | 29.2
Total |  |  |  | 73.52 | 98.24 | 171.76 |  | 61 | 45 | 12 | 4 | 62.77 | 66.61 | 129.38 | 67.8% |  | 189.06

## ABSTRACT HVDS Phase-I
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
HIGH VOLTAGE DISTRIBUTION SYSTEM (HVDS)
Physical Progress in respect of HVDS works entrusted on TTK basis under Rate Contract as on 31.01.2018
Sl No | Name of the Sub-division | R.C issued on | LOI issued on | No. of Proposed HVDS feeders | Project (LOI) Cost in Cr. | Revised Project cost as per RC in Crs. | Cummulative expenditure booked in crs | Work Status | Remarks
1 | Tumkur RSD–1 | 08.05.2013 | 21.03.2013 | 17 | 99.02 | 152.73 | 146.22 | Completed & commissioned
2 | Tumkur RSD-2 | 08.05.2013 | 21.03.2013 | 8 | 47.23 | 93.28 |  | Completed & commissioned
3 | Chikkaballapura | 08.05.2013 | 21.03.2013 | 6 | 34.8 | 74.62 | 57.54 | Completed & commissioned
4 | Doddaballapura | 20.02.2014 | 08.01.2014 | 9 | 193 | 87.64 | 87.63 | Completed & commissioned
5 | Tumkur RSD-1 | - | - | 8 | - | 75.26 | 298.81 | Completed & commissioned | 28 no's of feeders Re-designated from D.B pura & Kengeri
6 | Tumkur RSD-2 | - | - | 15 | - | 173.34 |  | Completed & commissioned
7 | CSD-3 Kyathsandra | - | - | 5 | - | 42.54 |  | Completed & commissioned
Total |  |  |  | 68 | 374.05 | 699.41 | 590.2

## ABSTRACT-HVDS P-II
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
HIGH VOLTAGE DISTRIBUTION SYSTEM (HVDS) PHASE-II
CUMULATIVE PHYSICAL PROGRESS OF HVDS WORKS
As on 31.01.2018
Sl. No. | Name of the Work | Unit | Qty as per DWA | Qty as per Survey | Progress as on prev month (Dec-2017) | Target fixed for the month of Jan-2018 | Progress for the month of Jan-2018 | Cumulative Progress as on Jan-2018 | % Physical progress against Survey Qty | % Physical progress against DWA Qty
1 | Extension of new 11KV line | KM's | 579.2545 | 722.0668 | 505.2362 | 216.8306 | 0 | 505.2362 | 69.97% | 87.22%
2 | Conversion of Existing LT line into HT line | KM's | 2878.9819 | 1184.502 | 847.7573 | 336.7447 | 0 | 847.7573 | 71.57% | 29.45%
3 | Running of New of 11KV line using AB cable | KM's | 25.8 | 32.23 | 10.16 | 22.07 | 0 | 10.16 | 31.52% | 39.38%
4 | Running of New LT line using LT AB size of 3X35+1X25 Sq mm | KM's | 471 | 639.92 | 365.943 | 273.977 | 0 | 365.943 | 57.19% | 77.69%
5 | Erection & Commissioning of 3Star 25kVA DTC’s | No's | 11406 | 13208 | 10076 | 3132 | 222 | 10298 | 77.97% | 90.29%
Note: The target date fixed for completion of the project is 18 months from the date of issue of DWA. Further, the completion period is extended up to 31.03.2018 & works are under progress.

## Kanaka USD (hidden)
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
HIGH VOLTAGE DISTRIBUTION SYSTEM (HVDS) PHASE-II
Name of Sub Division: Kanakapura Urban
Name of Executing Agency: M/s. SPR Construction, Hyderabad | [7 empty] | As on 31.01.2018
DWA Cost (Agency Portion): Rs. 24.14 Crores
Sl. No. | Name of the Work | Unit | Qty as per DWA | Qty as per Survey | Progress as on prev month (Dec-2017) | Target fixed for the month of Jan-2018 | Progress for the month of Jan-2018 | Cumulative Progress as on Jan-2018 | % Physical progress against Survey Qty | % Physical progress against DWA Qty
1 | Extension of new 11KV line | KM's | 135.2479 | 195.0082 | 170.33 | 24.6782 | 0 | 170.33 | 87.35% | 125.9%
2 | Conversion of Existing LT line into HT line | KM's | 1027.2578 | 302.3547 | 293 | 9.3547 | 0 | 293 | 96.91% | 28.52%
3 | Running of New of 11KV line using AB cable | KM's | 7 | 0.6 | 0 | 0.6 | 0 | 0 | 0% | 0%
4 | Running of New LT line using LT AB size of 3X35+1X25 Sq mm | KM's | 129 | 129 | 84 | 45 | 0 | 84 | 65.12% | 65.12%
5 | Erection & Commissioning of 3Star 25kVA DTC’s | No's | 3171 | 3499 | 3065 | 434 | 93 | 3158 | 90.25% | 99.59%
Note: The target date fixed for completion of the project is 18 months from the date of issue of DWA. Further, the completion period is extended up to 31.03.2018 & works are under progress.

## Kanaka RSD (hidden)
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
HIGH VOLTAGE DISTRIBUTION SYSTEM (HVDS) PHASE-II
Name of Sub Division: Kanakapura Rural
Name of Executing Agency: M/s. Raja Electricals, Tumkur | [7 empty] | As on 31.01.2018
DWA Cost (Agency Portion): Rs. 20.37 Crores
Sl. No. | Name of the Work | Unit | Qty as per DWA | Qty as per Survey | Progress as on prev month (Dec-2017) | Target fixed for the month of Jan-2018 | Progress for the month of Jan-2018 | Cumulative Progress as on Jan-2018 | % Physical progress against Survey Qty | % Physical progress against DWA Qty
1 | Extension of new 11KV line | KM's | 93.5961 | 181.9376 | 128.75 | 53.1876 | 0 | 128.75 | 70.77% | 137.6%
2 | Conversion of Existing LT line into HT line | KM's | 718.555 | 72.2496 | 46.7323 | 25.5172 | 0 | 46.7323 | 64.68% | 6.504%
3 | Running of New of 11KV line using AB cable | KM's | 6 | 6 | 5.55 | 0.45 | 0 | 5.55 | 92.5% | 92.5%
4 | Running of New LT line using LT AB size of 3X35+1X25 Sq mm | KM's | 41 | 51 | 46 | 5 | 0 | 46 | 90.2% | 112.2%
5 | Erection & Commissioning of 3Star 25kVA DTC’s | No's | 2426 | 2264 | 2118 | 146 | 102 | 2220 | 98.06% | 91.51%
Note: The target date fixed for completion of the project is 18 months from the date of issue of DWA. Further, the completion period is extended up to 31.03.2018 & works are under progress.

## Harohally (hidden)
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
HIGH VOLTAGE DISTRIBUTION SYSTEM (HVDS) PHASE-II
Name of Sub Division: Harohally
Name of Executing Agency: M/s. Shivachetana Electricals, Sindhanur | [7 empty] | As on 31.01.2018
DWA Cost (Agency Portion): Rs. 20.03 Crores
Sl. No. | Name of the Work | Unit | Qty as per DWA | Qty as per Survey | Progress as on prev month (Dec-2017) | Target fixed for the month of Jan-2018 | Progress for the month of Jan-2018 | Cumulative Progress as on Jan-2018 | % Physical progress against Survey Qty | % Physical progress against DWA Qty
1 | Extension of new 11KV line | KM's | 106.0755 | 149.8894 | 77.3 | 72.5894 | 0 | 77.3 | 51.57% | 72.87%
2 | Conversion of Existing LT line into HT line | KM's | 314.2857 | 182.86 | 138.8 | 44.06 | 0 | 138.8 | 75.91% | 44.16%
3 | Running of New of 11KV line using AB cable | KM's | 3.95 | 13.71 | 0 | 13.71 | 0 | 0 | 0% | 0%
4 | Running of New LT line using LT AB size of 3X35+1X25 Sq mm | KM's | 171 | 266.5 | 61.6 | 204.9 | 0 | 61.6 | 23.11% | 36.02%
5 | Erection & Commissioning of 3Star 25kVA DTC’s | No's | 2278 | 2724 | 1713 | 1011 | 27 | 1740 | 63.88% | 76.38%
Note: The target date fixed for completion of the project is 18 months from the date of issue of DWA. Further, the completion period is extended up to 31.03.2018 & works are under progress.

## Sathanur (hidden)
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
HIGH VOLTAGE DISTRIBUTION SYSTEM (HVDS) PHASE-II
Name of Sub Division: Sathanur
Name of Executing Agency: M/s. Sri Manju Electricals, Tumkur | [7 empty] | As on 31.01.2018
DWA Cost (Agency Portion): Rs. 17.05 Crores
Sl. No. | Name of the Work | Unit | Qty as per DWA | Qty as per Survey | Progress as on prev month (Dec-2017) | Target fixed for the month of Jan-2018 | Progress for the month of Jan-2018 | Cumulative Progress as on Jan-2018 | % Physical progress against Survey Qty | % Physical progress against DWA Qty
1 | Extension of new 11KV line | KM's | 65.6814 | 63.3826 | 38.6864 | 24.6962 | 0 | 38.6864 | 61.04% | 58.9%
2 | Conversion of Existing LT line into HT line | KM's | 466.1741 | 466.1741 | 242 | 224.1741 | 0 | 242 | 51.91% | 51.91%
3 | Running of New of 11KV line using AB cable | KM's | 1.5 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
4 | Running of New LT line using LT AB size of 3X35+1X25 Sq mm | KM's | 73 | 94 | 85.5 | 8.5 | 0 | 85.5 | 90.96% | 117.1%
5 | Erection & Commissioning of 3Star 25kVA DTC’s | No's | 1905 | 2994 | 1554 | 1440 | 0 | 1554 | 51.9% | 81.57%
Note: The target date fixed for completion of the project is 18 months from the date of issue of DWA. Further, the completion period is extended up to 31.03.2018 & works are under progress.

## Huliyur Durga (hidden)
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
HIGH VOLTAGE DISTRIBUTION SYSTEM (HVDS) PHASE-II
Name of Sub Division: Huliyurdurga
Name of Executing Agency: M/s. Sri. Lakshminarasimha Electricals, Tumkur | [7 empty] | As on 31.01.2018
DWA Cost (Agency Portion): Rs. 16.65 Crores
Sl. No. | Name of the Work | Unit | Qty as per DWA | Qty as per Survey | Progress as on prev month (Dec-2017) | Target fixed for the month of Jan-2018 | Progress for the month of Jan-2018 | Cumulative Progress as on Jan-2018 | % Physical progress against Survey Qty | % Physical progress against DWA Qty
1 | Extension of new 11KV line | KM's | 178.6535 | 131.8489 | 90.1698 | 41.6791 | 0 | 90.1698 | 68.39% | 50.47%
2 | Conversion of Existing LT line into HT line | KM's | 352.7094 | 160.8637 | 127.225 | 33.6388 | 0 | 127.225 | 79.09% | 36.07%
3 | Running of New of 11KV line using AB cable | KM's | 7.35 | 11.92 | 4.61 | 7.31 | 0 | 4.61 | 38.67% | 62.72%
4 | Running of New LT line using LT AB size of 3X35+1X25 Sq mm | KM's | 57 | 99.42 | 88.843 | 0 | 0 | 88.843 | 89.36% | 155.9%
5 | Erection & Commissioning of 3Star 25kVA DTC’s | No's | 1626 | 1727 | 1626 | 101 | 0 | 1626 | 94.15% | 100%
Note: The target date fixed for completion of the project is 18 months from the date of issue of DWA. Further, the completion period is extended up to 31.03.2018 & works are under progress.

## P & F Progress Phase-III (hidden)
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
HIGH VOLTAGE DISTRIBUTION SYSTEM (HVDS)
Physical & Financial Progress of HVDS Phase-III works awarded on TTK basis as on 31.01.2018
Sl. No. | Name of Division | Name of the Sub Division | Name of the firm | Awarded Cost (Rs. in Crores) |  |  | DWA issued on | No. of feeders Proposed | No. of Feeders Completed | No. of Feeders Commissioned | No. of feeders work under progress | Expenditure Incurred (Rs. in Crores) |  |  | Remarks
|  |  |  | BESCOM portion | DWA Cost (Agency) | Total | [5 empty] | BESCOM Portion | Agency Portion | Total
1 | Ramanagara | Ramanagar Rural | M/s. KGN Electricals, Tumkur | 0 | 46.25 | 46.25 | 03.06.2017 | 23 | 5 | 7 | 11 | 0 | 23.99 | 23.99 | Work under Progress | 45.38
2 |  | Channapatna Rural | M/s. Rajashree Electricals, Davanagere in JV with M/s. BVG India Ltd. | 0 | 62.25 | 62.25 | 03.06.2017 | 23 | 1 | 10 | 11 | 0 | 34.64 | 34.64 | Work under Progress | 64.03
3 |  | Channapatna Urban | M/s. Ramalingam Constructions Co. Pvt Ltd in JV with M/s Integrated Lighting Technologies Pvt., Ltd., | 0 | 53.53 | 53.53 | 26.10.2017 | 14 | 1 | 3 | 3 | 0 | 3.34 | 3.34 | Work under Progress | 35.84
4 |  | Bidadi |  | 0 |  |  |  | 5 | 0 | 0 | 2 |  |  |  |  | 16.9
Total |  |  |  | 0 | 162.03 | 162.03 |  | 65 | 7 | 20 | 27 | 0 | 61.97 | 61.97 |  | 162.15
0.38
162.53

## ABSTRACT-HVDS P-III
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
HIGH VOLTAGE DISTRIBUTION SYSTEM (HVDS) PHASE-II
CUMULATIVE PHYSICAL PROGRESS OF HVDS WORKS AS ON 31.01.2018
Sl. No. | Name of the Work | Unit | Qty as per DWA | Qty as per Survey | Progress as on prev month (Dec-2017) | Target fixed for the month of Jan-2018 | Progress for the month of Jan-2018 | Cumulative Progress as on Jan-2018 | % Physical progress against Survey Qty | % Physical progress against DWA Qty
1 | Extension of new 11KV line | KM's | 386.9228 | 391.757 | 174.7659 | 135 | 23.44 | 198.2059 | 50.59% | 51.23%
2 | Conversion of Existing LT line into HT line | KM's | 2021.1166 | 2284.6962 | 515.2512 | 215 | 84.0755 | 599.3268 | 26.23% | 29.65%
3 | Running of New of 11KV line using AB cable | KM's | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
4 | Running of New LT line using LT AB size of 3X35+1X25 Sq mm | KM's | 361.26 | 372.06 | 69.99 | 40 | 12.8 | 82.79 | 22.25% | 22.92%
5 | Erection & Commissioning of 3Star 25kVA DTC’s | No's | 12037 | 12751 | 3108 | 1100 | 872 | 3980 | 31.21% | 33.06%
Note: The target date fixed for completion of the project is 12 months from the date of issue of DWA.

## Ramanagar RSD (hidden)
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
HIGH VOLTAGE DISTRIBUTION SYSTEM (HVDS) PHASE-III
Name of Sub Division: Ramanagara Rural S/D
Name of Executing Agency: M/s. K.G.N Electricals, Tumkur | [7 empty] | As on 31.01.2018
DWA Cost (Agency Portion): Rs. 46.25 Crores
Sl. No. | Name of the Work | Unit | Qty as per DWA | Qty as per Survey | Progress as on prev month (Dec-2017) | Target fixed for the month of Jan-2018 | Progress for the month of Jan-2018 | Cumulative Progress as on Jan-2018 | % Physical progress against Survey Qty | % Physical progress against DWA Qty
1 | Extension of new 11KV line | KM's | 97.7668 | 80.2956 | 33.8259 | 10 | 0 | 33.8259 | 42.13% | 34.6%
2 | Conversion of Existing LT line into HT line | KM's | 697.3071 | 466.1412 | 271.4286 | 100 | 0 | 271.4286 | 58.23% | 38.93% | 554.5714
3 | Running of New of 11KV line using AB cable | KM's | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
4 | Running of New LT line using LT AB size of 3X35+1X25 Sq mm | KM's | 117.07 | 115.3 | 34.54 | 10 | 0 | 34.54 | 29.96% | 29.5% | 0
5 | Erection & Commissioning of 3Star 25kVA DTC’s | No's | 3438 | 3343 | 614 | 500 | 155 | 769 | 23% | 22.37% | -155
Note: The target date fixed for completion of the project is 12 months from the date of issue of DWA. The DWA is issued on 03.06.2017

## Channapatna RSD (hidden)
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
HIGH VOLTAGE DISTRIBUTION SYSTEM (HVDS) PHASE-III
Name of Sub Division: Channapatna Rural S/D | [7 empty] | As on 31.01.2018
Name of Executing Agency: M/s. Rajashree Electricals, Davanagere in JV with M/s. BVG India Ltd.
DWA Cost (Agency Portion): Rs. 62.25 Crores
Sl. No. | Name of the Work | Unit | Qty as per DWA | Qty as per Survey | Progress as on prev month (Dec-2017) | Target fixed for the month of Jan-2018 | Progress for the month of Jan-2018 | Cumulative Progress as on Jan-2018 | % Physical progress against Survey Qty | % Physical progress against DWA Qty
1 | Extension of new 11KV line | KM's | 158.4959 | 163.6782 | 104.6 | 100 | 23.44 | 128.04 | 78.23% | 80.78% | -23.44
2 | Conversion of Existing LT line into HT line | KM's | 742.4631 | 946.6338 | 181.0969 | 100 | 64.0427 | 245.1396 | 25.9% | 33.02%
3 | Running of New of 11KV line using AB cable | KM's | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
4 | Running of New LT line using LT AB size of 3X35+1X25 Sq mm | KM's | 178.49 | 176.76 | 35.45 | 25 | 12.8 | 48.25 | 27.3% | 27.03%
5 | Erection & Commissioning of 3Star 25kVA DTC’s | No's | 4466 | 5273 | 2339 | 500 | 707 | 3046 | 57.77% | 68.2%
Note: The target date fixed for completion of the project is 12 months from the date of issue of DWA. The DWA is issued on 03.06.2017

## CN Patna USD & Bidadi (hidden)
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
HIGH VOLTAGE DISTRIBUTION SYSTEM (HVDS) PHASE-III
Name of Sub Division: Channapatna Urban & Bidadi S/D | [7 empty] | As on 31.01.2018
Name of Executing Agency: M/s. Ramalingam Constructions Co. Pvt Ltdin JV with M/s Integrated Lighting Technologies Pvt., Ltd.,
DWA Cost (Agency Portion): Rs. 53.53 Crores
Sl. No. | Name of the Work | Unit | Qty as per DWA | Qty as per Survey | Progress as on prev month (Dec-2017) | Target fixed for the month of Jan-2018 | Progress for the month of Jan-2018 | Cumulative Progress as on Jan-2018 | % Physical progress against Survey Qty | % Physical progress against DWA Qty
1 | Extension of new 11KV line | KM's | 130.6601 | 147.7833 | 36.34 | 25 | 0 | 36.34 | 24.59% | 27.81%
2 | Conversion of Existing LT line into HT line | KM's | 581.3465 | 871.9212 | 62.7258 | 15 | 20.0328 | 82.7586 | 9.492% | 14.24%
3 | Running of New of 11KV line using AB cable | KM's | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
4 | Running of New LT line using LT AB size of 3X35+1X25 Sq mm | KM's | 65.7 | 80 | 0 | 5 | 0 | 0 | 0% | 0%
5 | Erection & Commissioning of 3Star 25kVA DTC’s | No's | 4133 | 4135 | 155 | 100 | 10 | 165 | 3.99% | 3.992%
Note: The target date fixed for completion of the project is 12 months from the date of issue of DWA. Due to delay in submission of CPG by agency, the DWA have been issued on 26.10.2017