## Slide 1
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Integrated Power Development Scheme
Name of Executing Agency: M/s. Maruthi Mechanicals & Electricals(P) Ltd., /Bangalore. |  |  |  |  |  | 
DWA Amount: Rs. 9.418 Crores |  |  |  |  |  | 
Name of Circle : BANGALORE RURAL Date of Completion: 07.01.2019 |  |  |  |  |  | 
S. No. | Nature of work | UoM | DWA Qty | Approved Survey Qty | Target Qty for the FY 2017-18 (March-2018) against survey quantity | Target for the month of Jan-18 | Progress till Dec-2017 | Progress during month of Jan- 2018 | Cumulative progress as at the end of Jan-18 | % Progress w.r.t. Progress of Jan-18 & Target fixed for FY-2017-18
1 | Running of 11KV over head line "(New and Re-conductoring) | km | 20.6 | 20.6 | 10.3 | 2.06 | 2.40 | 0.146 | 2.546 | 24.72%
2 | Running of 11KV Aerial Bunched Cable" (New and Re-conductoring) | km | 21.1 | 21.06 | 10.53 | 2.11 | 6.18 | 0.0 | 6.175 | 58.64%
3 | Providing 11KV Underground cable | km | 5.9 | 5.9 | 2.95 | 0.59 | 0.00 | 0.0 | 0.0 | 0.00%
4 | Installation of New DTCs | Nos | 64 | 64 | 32 | 6.40 | 11.00 | 1 | 12.0 | 37.50%
5 | Capacity Enhancement of DTCs | Nos | 0 | 0 | 0 | 0.00 | 0.00 | 0 | 0.0 | 0.00%
6 | Running of LT over head line "(New and Re-conductoring) | km | 118 | 118 | 59 | 11.80 | 0.00 | 0.0 | 0.0 | 0.00%
7 | Running of LT Aerial Bunched Cable (New and Re-conductoring) | km | 18.9 | 18.9 | 9.45 | 1.89 | 9.03 | 0.275 | 9.3 | 98.41%
8 | Providing LT Underground cable | km | 0 | 0 | 0 | 0.00 | 0.00 | 0.0 | 0.0 | 0.00%

## Slide 2
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Integrated Power Development Scheme
Name of Executing Agency: M/s. Asian Fab Tech Ltd., /Bangalore. |  |  |  |  |  | 
DWA Amount: Rs. 48.24 Crores |  |  |  |  |  | 
Name of Circle : RAMANAGARA Date of Completion: 23.03.2019 |  |  |  |  |  | 
S. No. | Nature of work | UoM | DWA Qty | Approved Survey Qty | Target Qty for the FY 2017-18 (March-2018) against survey quantity | Target for the month of Jan-18 | Progress till Dec-2017 | Progress during month of Jan- 2018 | Cumulative progress as at the end of Jan-18 | % Progress w.r.t. Progress of Jan-18 & Target fixed for FY-2017-18
1 | Running of 11KV over head line "(New and Re-conductoring) | km | 4.93 | 33.8 | 16.9 | 3.38 | 0.00 | 0.33 | 0.33 | 1.95%
2 | Running of 11KV Aerial Bunched Cable" (New and Re-conductoring) | km | 16.8 | 0 | 0 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00%
3 | Providing 11KV Underground cable | km | 106 | 107.47 | 53.735 | 10.75 | 31.48 | 9.78 | 41.26 | 76.78%
4 | Installation of New DTCs | Nos | 186 | 82 | 41 | 8.20 | 14.00 | 0 | 14.00 | 34.15%
5 | Capacity Enhancement of DTCs | Nos | 49 | 93 | 47 | 9.40 | 10.00 | 0 | 10.00 | 21.28%
6 | Running of LT over head line "(New and Re-conductoring) | km | 17.7 | 14.5 | 7.25 | 1.45 | 7.50 | 0.00 | 7.50 | 103.45%
7 | Running of LT Aerial Bunched Cable (New and Re-conductoring) | km | 16.8 | 3.6 | 1.8 | 0.36 | 2.50 | 0.00 | 2.50 | 138.89%
8 | Providing LT Underground cable | km | 4.20 | 9.3 | 4.65 | 0.93 | 0.00 | 0.00 | 0.00 | 0.00%

## Slide 3
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Integrated Power Development Scheme
Name of Executing Agency: M/s. Tranglobal Power Limited, Bangalore |  |  |  |  |  | 
DWA Amount: Rs. 53.625 Crores |  |  |  |  |  | 
Name of Circle : KOLAR Date of Completion: 07.01.2019 |  |  |  |  |  | 
S. No. | Nature of work | UoM | DWA Qty | Approved Survey Qty | Target Qty for the FY 2017-18 (March-2018) against survey quantity | Target for the month of Jan-18 | Progress till Dec-2017 | Progress during month of Jan- 2018 | Cumulative progress as at the end of Jan-18 | % Progress w.r.t. Progress of Jan-18 & Target fixed for FY-2017-18
1 | Running of 11KV over head line "(New and Re-conductoring) | km | 241.71 |  | 120.855 | 24.17 | 0.95 | 3.5 | 4.45 | 3.68%
2 | Running of 11KV Aerial Bunched Cable" (New and Re-conductoring) | km | 65.13 |  | 32.565 | 6.513 | 1.78 | 3.6 | 5.38 | 16.52%
3 | Providing 11KV Underground cable | km | 21.96 |  | 10.98 | 2.196 | 0.00 | 0.0 | 0.0 | 0 %
4 | Installation of New DTCs | Nos | 138 |  | 69 | 14 | 0.00 | 3 | 3.0 | 4.34%
5 | Capacity Enhancement of DTCs | Nos | 106 |  | 53 | 11 | 0.00 | 0 | 0.0 | 0%
6 | Running of LT over head line "(New and Re-conductoring) | km | 697.49 |  | 348.745 | 69.75 | 106.00 | 46.8 | 152.77 | 43.78%
7 | Running of LT Aerial Bunched Cable (New and Re-conductoring) | km | 263 |  | 131.5 | 52.6 | 0.00 | 3.185 | 3.185 | 2.42 %
8 | Providing LT Underground cable | km | 1.96 |  | 0.98 | 0.196 | 0.00 | 0.0 | 0.0 | 0%

## Slide 4
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Integrated Power Development Scheme
Name of Executing Agency: M/s. L&T Ltd., Chennai |  |  |  |  |  | 
DWA Amount: Rs. 116.356 Crores |  |  |  |  |  | 
Name of Circle : DAVANAGERE Date of Completion: 07.01.2019 |  |  |  |  |  | 
S. No. | Nature of work | UoM | DWA Qty | Approved Survey Qty | Target Qty for the FY 2017-18 (March-2018) against survey quantity | Target for the month of Jan-18 | Progress till Dec-2017 | Progress during month of Jan- 2018 | Cumulative progress as at the end of Jan-18 | % Progress w.r.t. Progress of Jan-18 & Target fixed for FY-2017-18
1 | Running of 11KV over head line "(New and Re-conductoring) | km | 263.49 | 103.35 | 51.675 | 10.34 | 5.49 | 6.81 | 12.30 | 23.80%
2 | Running of 11KV Aerial Bunched Cable" (New and Re-conductoring) | km | 51.36 | 50 | 25 | 5.00 | 0.00 | 1.49 | 1.49 | 5.96%
3 | Providing 11KV Underground cable | km | 98 | 98 | 49 | 9.80 | 65.03 | 2.9 | 67.9 | 138.63%
4 | Installation of New DTCs | Nos | 508 | 459 | 229.5 | 45.90 | 0.00 | 0 | 0.0 | 0.00%
5 | Capacity Enhancement of DTCs | Nos | 95 | 108 | 54 | 10.80 | 0.00 | 0 | 0.0 | 0.00%
6 | Running of LT over head line "(New and Re-conductoring) | km | 214.34 | 333.4 | 166.7 | 33.34 | 22.68 | 29.92 | 52.60 | 31.55%
7 | Running of LT Aerial Bunched Cable (New and Re-conductoring) | km | 26.91 | 27.95 | 13.975 | 2.80 | 0.00 | 0.000 | 0.000 | 0.00%
8 | Providing LT Underground cable | km | 56 | 59.67 | 29.835 | 5.97 | 0.00 | 3.4 | 3.4 | 11.40%

## Slide 5
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Integrated Power Development Scheme
Name of Executing Agency: M/s. Bajaj Electricals Limited, Mumbai |  |  |  |  |  | 
DWA Amount: Rs. 55.252 Crores |  |  |  |  |  | 
Name of Circle : TUMKUR Date of Completion: 07.01.2019 |  |  |  |  |  | 
S. No. | Nature of work | UoM | DWA Qty | Approved Survey Qty | Target Qty for the FY 2017-18 (March-2018) against survey quantity | Target for the month of Jan-18 | Progress till Dec-2017 | Progress during month of Jan- 2018 | Cumulative progress as at the end of Jan-18 | % Progress w.r.t. Progress of Jan-18 & Target fixed for FY-2017-18
1 | Running of 11KV over head line "(New and Re-conductoring) | km | 287.10 | 195.63 | 97.815 | 19.56 | 9.49 | 12.10 | 21.59 | 22.07%
2 | Running of 11KV Aerial Bunched Cable" (New and Re-conductoring) | km | 123.3 | 107.09 | 53.545 | 10.71 | 0.00 | 1.10 | 1.10 | 2.05%
3 | Providing 11KV Underground cable | km | 46.41 | 36.32 | 18.16 | 3.63 | 0.00 | 0.0 | 0.00 | 0.00%
4 | Installation of New DTCs | Nos | 370 | 370 | 185 | 37.00 | 0.00 | 79 | 79.00 | 42.70%
5 | Capacity Enhancement of DTCs | Nos | 216 | 216 | 108 | 21.60 | 0.00 | 0 | 0.00 | 0.00%
6 | Running of LT over head line "(New and Re-conductoring) | km | 716.52 | 585.6 | 292.8 | 58.56 | 28.95 | 52.50 | 81.45 | 27.82%
7 | Running of LT Aerial Bunched Cable (New and Re-conductoring) | km | 128.1 | 116.87 | 58.435 | 11.69 | 6.30 | 20.120 | 26.42 | 45.21%
8 | Providing LT Underground cable | km | 0 | 0 | 0 | 0.00 | 0.00 | 0.0 | 0.00 | 0.00%

## Slide 6
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
Integrated Power Development Scheme
Name of Executing Agency: M/s. L&T Ltd., Chennai |  |  |  |  |  | 
DWA Amount: Rs. 196.104 Crores |  |  |  |  |  | 
Name of Circle : BMAZ Date of Completion: 07.01.2019 |  |  |  |  |  | 
S. No. | Nature of work | UoM | DWA Qty | Approved Survey Qty | Target Qty for the FY 2017-18 (March-2018) against survey quantity | Target for the month of Jan-18 | Progress till Dec-2017 | Progress during month of Jan- 2018 | Cumulative progress as at the end of Jan-18 | % Progress w.r.t. Progress of Jan-18 & Target fixed for FY-2017-18
1 | Running of 11KV over head line "(New and Re-conductoring) | km | 151.26 |  | 75.63 | 5.68 | 0.00 | 0.00 | 0.00 | 0.00%
2 | Running of 11KV Aerial Bunched Cable" (New and Re-conductoring) | km | 3.80 |  | 1.9 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00%
3 | Providing 11KV Underground cable | km | 453.53 |  | 227.5 | 20.60 | 101.20 | 18.54 | 117.06 | 51.62 %
4 | Installation of New DTCs | Nos | 0.00 |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00%
5 | Capacity Enhancement of DTCs | Nos | 0.00 |  | 0 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00%
6 | Running of LT over head line "(New and Re-conductoring) | km | 166.90 |  | 83.5 | 8.48 | 0.00 | 0.00 | 0.00 | 0.00%
7 | Running of LT Aerial Bunched Cable (New and Re-conductoring) | km | 64.11 |  | 32.10 | 3.09 | 0.00 | 0.00 | 0.00 | 0.00%
8 | Providing LT Underground cable | km | 20.10 |  | 10.10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00%