## Slide 1
ABSTRACT of NJY Phase -1 Scheme |  |  |  |  | 
SL. NO. | Circle | NO. of Proposed NJY FEEDERS | NO. OF FEEDERS COMMISSIONED | Balance feeders to be Commissioned | Remarks
1 | Kolar (Malur Pilot Project) | 10 | 10 | Nil | Commissioned (March-2014)
2 | BRC | 60 | 60 | Nil | 
3 | Kolar | 25 | 25 | Nil | 
4 | Tumkur | 99 | 99 | Nil | 
5 | Davangere | 77 | 77 | Nil | 
Total |  | 271 | 271 |  | 

## Slide 2
ABSTRACT of NJY Phase -2 Scheme |  |  |  |  | 
SL. NO. | Circle | NO. of Proposed NJY FEEDERS | NO. OF FEEDERS COMMISSIONED | Balance feeders to be Commissioned | Remarks
1 | BRC | 18 | 18 | Nil | Commissioned (Feb-2017)
2 | Ramanagara | 14 | 14 | Nil | 
3 | Kolar | 109 | 109 | Nil | 
4 | Tumkur | 63 | 63 | Nil | 
5 | Davangere | 77 | 77 | Nil | 
Total |  | 281 | 281 |  | 

## Slide 3: STATUS OF NIRANTHARA JYOTHI – Phase-3 at the end of Dec-2017
Sl. | Name of the Circle/ Division | PTK No./ DWA/LOI/SDC date | Name of the bidder | NO. of Proposed NJY FEEDERS | Cumulative progress |  | Progress as on Aug 2017 |  | Achievement |  | Balance No. of Feeders to be |  | Remarks
 |  |  |  |  | NO. OF FEEDERS Completed as at the End of 01.12.2017 | NO. OF FEEDERS COMMISSIONED as at the End of 01.12.2017 | NO. OF FEEDERS Completed as at the End of 01.08.2017 | NO. OF FEEDERS COMMISSIONED as at the End of 01.08.2017 | No of Feeders completed From 1.8.17 to 01.12.17 | No of Feeders commissioned From 1.8.17 to 01.12.17 |  |  | 
 |  |  |  |  |  |  |  |  |  |  | completed | commissioned | 
 |  |  |  | A | B=D+H | C=E+I | D | E | H | I | J=A-B | K=A-C | 
1 | Madhugiri | PTK-90 LOI 21.10.15 DWA 26.11.15 SDC 21.1.17 | M/s KGN Electricals | 51 | 51 | 51 | 51 | 51 | 0 | 0 | 0 | 0 | 
2 | BRC | PTK-93 LOI 21.10.15 DWA 26.11.15 SDC 21.1.17 | M/s BVG India Pvt. Ltd, Pune | 22 | 17 | 14 | 14 | 10 | 3 | 4 | 5 | 8 | Individual feeder wise status is Enclosed
 |  |  |  | 27 | 18 | 10 | 13 | 8 | 5 | 2 | 9 | 17 | 
 | Ramanagara |  |  |  |  |  |  |  |  |  |  |  | 
3 | Ramanagara | PTK-94/ LOI 21.10.15 DWA 26.11.15 SDC 21.1.17 | M/s Asian Fab Tec Ltd., | 62 | 57 | 53 | 55 | 37 | 2 | 16 | 5 | 9 | 

## Slide 4
Sl. | Name of the Circle/ Division | PTK No./ DWA/LOI/SDC date | Name of the bidder | NO. of Proposed NJY FEEDERS | Cumulative progress |  | Progress as on Aug 2017 |  | Achievement |  | Balance No. of Feeders to be |  | Remarks
 |  |  |  |  | NO. OF FEEDERS Completed as at the End of 01.12.2017 | NO. OF FEEDERS COMMISSIONED as at the End of 01.12.2017 | NO. OF FEEDERS Completed as at the End of 01.08.2017 | NO. OF FEEDERS COMMISSIONED as at the End of 01.08.2017 | No of Feeders completed From 1.8.17 to 01.12.17 | No of Feeders commissioned From 1.8.17 to 01.12.17 |  |  | 
 |  |  |  |  |  |  |  |  |  |  | completed | commissioned | 
 |  |  |  | A | B=D+H | C=E+I | D | E | H | I | J=A-B | K=A-C | 
4 | Kolar | PTK-95/ LOI 21.10.15 DWA 26.11.15 SDC 21.1.17 | M/s Pawani Controls & Panels Ltd, Hyderabad | 64 | 59 | 57 | 36 | 34 | 23 | 23 | 5 | 7 | Individual feeder wise status is Enclosed
5 | Tumkur & Tiptur Div. | PTK-96/ LOI 16.12.15 DWA 20.1.16 SDC 16.3.17 | M/s Tranaglobal Power Ltd., Bangalore | 87 | 85 | 84 | 79 | 76 | 6 | 8 | 2 | 3 | 
6 | Davangere | PTK-97/ LOI 16.12.15 DWA 20.1.16 SDC 16.3.17 | M/s Asian Fab Tec Ltd., | 101 | 86 | 61 | 83 | 48 | 3 | 13 | 15 | 40 | 
Grand Total |  |  |  | 414 | 373 | 330 | 331 | 264 | 42 | 66 | 41 | 84 | 

## Slide 5: STATUS OF NIRANTHARA JYOTHI – Phase-3 at the end of January -2018
Sl. | Name of the Circle/ Division | PTK No./ DWA/LOI/SDC date | Name of the bidder | NO. of Proposed NJY FEEDERS | Cumulative progress |  | Progress as on Aug 2017 |  | Achievement |  | Balance No. of Feeders to be |  | Remarks
 |  |  |  |  | NO. OF FEEDERS Completed as at the End of 24.1.2018 | NO. OF FEEDERS COMMISSIONED as at the End of 24.1.2018 | NO. OF FEEDERS Completed as at the End of 01.08.2017 | NO. OF FEEDERS COMMISSIONED as at the End of 01.08.2017 | No of Feeders completed From 1.8.17 to 24.01.18 | No of Feeders commissioned From 1.8.17 to 24.01.18 |  |  | 
 |  |  |  |  |  |  |  |  |  |  | completed | commissioned | 
 |  |  |  | A | B=D+H | C=E+I | D | E | H | I | J=A-B | K=A-C | 
1 | Madhugiri | PTK-90 LOI 21.10.15 DWA 26.11.15 SDC 21.1.17 | M/s KGN Electricals | 51 | 51 | 51 | 51 | 51 | 0 | 0 | 0 | 0 | 
2 | BRC | PTK-93 LOI 21.10.15 DWA 26.11.15 SDC 21.1.17 | M/s BVG India Pvt. Ltd, Pune | 22 | 17 | 14 | 14 | 10 | 3 | 4 | 5 | 8 | Individual feeder wise status is Enclosed
 |  |  |  | 27 | 19 | 12 | 13 | 8 | 6 | 4 | 8 | 15 | 
 | Ramanagara |  |  |  |  |  |  |  |  |  |  |  | 
3 | Ramanagara | PTK-94/ LOI 21.10.15 DWA 26.11.15 SDC 21.1.17 | M/s Asian Fab Tec Ltd., | 62 | 58 | 54 | 55 | 37 | 3 | 17 | 4 | 8 | 

## Slide 6
Sl. | Name of the Circle/ Division | PTK No./ DWA/LOI/SDC date | Name of the bidder | NO. of Proposed NJY FEEDERS | Cumulative progress |  | Progress as on Aug 2017 |  | Achievement |  | Balance No. of Feeders to be |  | Remarks
 |  |  |  |  | NO. OF FEEDERS Completed as at the End of 24.1.2018 | NO. OF FEEDERS COMMISSIONED as at the End of 24.1.2018 | NO. OF FEEDERS Completed as at the End of 01.08.2017 | NO. OF FEEDERS COMMISSIONED as at the End of 01.08.2017 | No of Feeders completed From 1.8.17 to 24.1.18 | No of Feeders commissioned From 1.8.17 to 24.1.18 |  |  | 
 |  |  |  |  |  |  |  |  |  |  | completed | commissioned | 
 |  |  |  | A | B=D+H | C=E+I | D | E | H | I | J=A-B | K=A-C | 
4 | Kolar | PTK-95/ LOI 21.10.15 DWA 26.11.15 SDC 21.1.17 | M/s Pawani Controls & Panels Ltd, Hyderabad | 64 | 61 | 59 | 36 | 34 | 25 | 25 | 3 | 5 | Individual feeder wise status is Enclosed
5 | Tumkur & Tiptur Div. | PTK-96/ LOI 16.12.15 DWA 20.1.16 SDC 16.3.17 | M/s Tranaglobal Power Ltd., Bangalore | 87 | 86 | 84 | 79 | 76 | 7 | 8 | 1 | 3 | 
6 | Davangere | PTK-97/ LOI 16.12.15 DWA 20.1.16 SDC 16.3.17 | M/s Asian Fab Tec Ltd., | 101 | 92 | 81 | 83 | 48 | 9 | 33 | 9 | 20 | 
Grand Total |  |  |  | 414 | 384 | 355 | 331 | 264 | 53 | 91 | 30 | 59 | 

## Slide 7
Thank you