## Slide 1
Overall Progress of Replacement of DTCs on footpath as per new design and Shifting of DTCs from footpath to CA site
Sl No | Circle | DTCs name & No for which Award is placed | Work Order number and date | Value of work award | Expected completion date | Expenditure booked for Dec-17 | Cumulative Expenditure booked
1 | South | Estimate preparation under process & Awaiting for budget. |  |  |  |  | 
2 | North |  |  |  |  |  | 
3 | East |  |  |  |  |  | 
4 | West |  |  |  |  |  | 

## Slide 2
Physical Progress of Providing DTCs as per new design by replacing the existing DTCs on footpath
Sl No | Circle | No: of DTCs to be provided as per design | No: of DTCs provided as per design on Dec-2017 | Cumulative DTCs provided as per design | Balance | Remarks
1 | South | 896 | 4 | 7 | 889 | 
2 | North | 939 | 33 | 33 | 906 | 
3 | East | 1478 | 35 | 82 | 1396 | 
4 | West | 605 | 0 | 2 | 603 | 
TOTAL |  | 3918 | 48 | 135 | 3783 | 

## Slide 3
Physical Progress of Shifting of DTCs on Footpath to Convenient locations
Sl No | Circle | No: of DTCs to be shifted | No: of DTCs shifted in Dec-2017 | Cumulative DTCs shifted | Balance | Remarks
1 | South | 31 | 0 | 0 | 31 | 
2 | North | 44 | 0 | 0 | 44 | 
3 | East | 21 | 0 | 0 | 21 | 
4 | West | 0 | 0 | 0 | 0 | 
Total |  | 96 | 0 | 0 | 96 |