## Sheet1
Physical Progress of Shifting of DTCs on Footpath to Convenient locations
Sl No | Circle | No: of DTCs to be shifted | No: of DTCs shifted in Dec-2017 | Cumulative DTCs shifted | Balance | Remarks
1 | South | 31 | 15 | 5 | 31
2 | North | 44 | 5 | 15 | 44
3 | East | 21 | 20 | 12 | 21
4 | West | 0 | 12 | 12 | 0
5 | Total | 96 | 52 | 44 | 96