## Sheet1
BANGALORE ELECTRICITY SUPPLY COMPANY LIMITED
CUMULATIVE PHYSICAL PROGRESS OF WORKS PROPOSED UNDER DDUGJY SCHEME IN 8 DISTRICTS IN THE JURISDICTION OF BESCOM UNDER TOTAL TURNKEY CONTRACT
DEENA DAYAL UPADHYAYA GRAMA JYOTHI YOJANA
S.No | Nature of Works | UNIT | DWA QTY | FIELD SURVEY QTY | TARGET as on MAR-18 | TARGET FIXED FOR DEC-17 | PROGRESS ACHIVED FOR DEC-17 | PROGRESS FOR THE MONTH OF JAN-18 | CUMULATIVE PROGRESS AS AT THE END OF Dec-17 | % OF PROGRESS AS ON DEC-17 (TARGET MAR-18)
A | SYSTEM STRENGTHENING
1 | Running of New 11kV Line | KM's | 404.1 | 343.07 | 202.05 | 34 | 26.9 | 6 | 103 | 50.97%
2 | Re-conductoring of 11kV Line | KM's | 117.33 | 122.53 | 58.66 | 0 | 6 | 0 | 70 | 119.3%
B | RURAL ELECTRIFICATION WITH INFRASTRUCTURE
3 | RunningRural of New 11kV Line | KM's | 4 | 1.9 | 2 | 0.12 | 0.3 | 0 | 2 | 100%
4 | Running of New LT Line | KM's | 6.14 | 0 | 3.07 | 0.77 | 0.6 | 0 | 1.2 | 39.09%
5 | Providing Rural New DTC | No's | 8 | 0 | 4 | 1 | 0 | 0 | 0 | 0%
6 | Augmentation of DTC | No's
7 | Providing Service connection Rural to BPL households | No's | 5766 | 650 | 2883 | 716 | 8 | 32 | 8 | 0.27%
C | SANSAD ADARSH GRAMA YOJANA (SAGY)
8 | Running San of New 11kV Line | KM's | 32.11 | 0 | 32.11 | 7 | 5.3 | 8 | 5.3 | 16.5%
9 | Running San of New LT Line | KM's | 13 | 13 | 13 | 3 | 0 | 0 | 5 | 38.47%
10 | Re-conductoring San of LT Line | KM's | 8 | 8 | 8 | 2 | 0 | 0 | 0 | 0%
11 | Providing New DTC | No's | 52 | 0 | 52 | 13 | 0 | 0 | 0 | 0%
12 | Augmentation San of DTC | No's |  |  | 0
13 | Providing Service Rural connection to BPL households | No's | 119 | 0 | 119 | 30 | 0 | 0 | 0 | 0%
14 | Providing Earthing for Existing DTC | No's | 90 | 90 | 90 | 21 | 0 | 0 | 28 | 31.11%

## Sheet2
1
2
3
4
5