## Sheet1
STATUS OF NIRANTHARA JYOTHI – Phase-3 at the end of Dec-2017
Sl. | Name of the Circle/ Division | PTK No./ DWA/LOI/SDC date | Name of the bidder | NO. of Proposed NJY FEEDERS | Cumulative progress |  | Progress as on Aug 2017 |  | Achievement |  | Balance No. of Feeders to be |  | Remarks
[5 empty] | NO. OF FEEDERS Completed as at the End of 01.12.2017 | NO. OF FEEDERS COMMISSIONED as at the End of 01.12.2017 | NO. OF FEEDERS Completed as at the End of 01.08.2017 | NO. OF FEEDERS COMMISSIONED as at the End of 01.08.2017 | No of Feeders completed From 1.8.17 to 01.12.17 | No of Feeders commissioned From 1.8.17 to 01.12.17
[11 empty] | completed | commissioned
|  |  |  | A | B=D+H | C=E+I | D | E | H | I | J=A-B | K=A-C
1 | Madhugiri | PTK-90 LOI 21.10.15 DWA 26.11.15 SDC 21.1.17 | M/s KGN Electricals | 51 | 51 | 51 | 51 | 51 | 0 | 0 | 0 | 0
2 | BRC | PTK-93 LOI 21.10.15 DWA 26.11.15 SDC 21.1.17 | M/s BVG India Pvt. Ltd, Pune | 22 | 17 | 14 | 14 | 10 | 3 | 4 | 5 | 8 | Individual feeder wise status is Enclosed
|  |  |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
Ramanagara
3 | Ramanagara | PTK-94/ LOI 21.10.15 DWA 26.11.15 SDC 21.1.17 | M/s Asian Fab Tec Ltd., | 62 | 57 | 53 | 55 | 37 | 2 | 16 | 5 | 9
4 | Kolar | PTK-95/ LOI 21.10.15 DWA 26.11.15 SDC 21.1.17 | M/s Pawani Controls & Panels Ltd, Hyderabad | 64 | 59 | 57 | 36 | 34 | 23 | 23 | 5 | 7 | Individual feeder wise status is Enclosed
5 | Tumkur & Tiptur Div. | PTK-96/ LOI 16.12.15 DWA 20.1.16 SDC 16.3.17 | M/s Tranaglobal Power Ltd., Bangalore | 87 | 85 | 84 | 79 | 76 | 6 | 8 | 2 | 3
6 | Davangere | PTK-97/ LOI 16.12.15 DWA 20.1.16 SDC 16.3.17 | M/s Asian Fab Tec Ltd., | 101 | 86 | 61 | 83 | 48 | 3 | 13 | 15 | 40